RESEARCH & ENGINEERING DOCUMENTATION

Critical Evaluation of EEG Biomarkers for Alzheimer's Disease

with Minimal-Electrode Machine Learning Optimization

Dataset: OpenNeuro ds004504, snapshot v1.0.9

Primary benchmark: DICE-Net (Miltiadous et al., IEEE Access, 2023)

Version 1.0  |  20 August 2026

Purpose

A reproducible, leakage-safe workflow for replicating, challenging, and engineering EEG biomarkers of dementia.

# Contents

1. Executive Summary

2. Project Charter

3. Scientific Background and Research Gap

4. Research Questions, Aims, and Hypotheses

5. Dataset Specification

6. Study Design: Replication Track vs Critique Track

7. Software Environment and Repository Architecture

8. Data Ingestion and Quality Control

9. Epoching and Subject-Level Sampling

10. DICE-Net Biomarker Replication

11. Spectral Biomarker Critique

12. Connectivity Biomarker Critique

13. Disease Specificity and Clinical Relevance

14. Statistical Analysis Plan

15. Machine-Learning Plan

16. Validation and Leakage Prevention

17. Robust Biomarker Decision Framework

18. Minimal-Electrode Optimization

19. Sensitivity and Robustness Analyses

20. Figures, Tables, and Reporting Standards

21. Milestones and Execution Order

22. Risk Register and Mitigation

23. Reproducibility, Ethics, and Claims

24. Definition of Done

Appendix A. Configuration Template

Appendix B. Command-Line Workflow

Appendix C. Data Dictionaries

Appendix D. Analysis Checklists

References

Core rule: Do not optimize the reduced montage until the biomarker critique is complete. The project first asks which biomarkers are defensible, then asks how few electrodes are needed to preserve them.

# 1. Executive Summary

This project will reproduce two EEG feature families used in DICE-Net - Relative Band Power (RBP) and Spectral Coherence Connectivity (SCC) - on the same 88-subject resting-state EEG dataset, then systematically test whether these proposed biomarkers remain meaningful when their major methodological assumptions are challenged. The final engineering stage will identify a reduced electrode montage that preserves both subject-level classification performance and the robust physiological information that survives the critique.

The project is intentionally not framed as "build the highest-accuracy Alzheimer classifier." Instead, it asks whether commonly used EEG biomarkers are stable, disease-specific, physiologically interpretable, and useful under rigorous subject-level validation. This creates a stronger Biomedical Engineering (BME) contribution: the output is a defensible measurement strategy and a minimal sensing configuration, not only a prediction model.

| Stage | Question | Primary output |
| --- | --- | --- |
| Replication | Can we reproduce RBP/SCC patterns from DICE-Net? | Matched baseline features and subject-level results |
| Spectral critique | Are fixed-band RBP effects robust to IAF and periodic/aperiodic decomposition? | Validated spectral biomarker set |
| Connectivity critique | Do SCC effects persist with less zero-lag-sensitive connectivity metrics? | Validated connectivity biomarker set |
| Specificity | Are features AD-specific or markers of neurodegeneration/cognitive impairment? | AD-CN, FTD-CN, and AD-FTD comparison matrix |
| Machine learning | Which feature families add reproducible predictive value? | Nested-CV subject-level benchmark |
| Engineering | How few electrodes preserve robust biomarker information? | Minimal biologically faithful montage |

## Project endpoint

The preferred final result is not necessarily the smallest possible montage. It is the smallest montage that meets pre-specified performance and biomarker-preservation requirements, with uncertainty reported across outer validation folds. If a 4-channel montage classifies well but loses physiologically meaningful information while a 6-channel montage preserves it, the engineering conclusion should favor the 6-channel configuration.

# 2. Project Charter

## 2.1 Problem statement

EEG-based dementia studies frequently use canonical spectral power and coherence as biomarkers. These measures are attractive because they are inexpensive, interpretable, and compatible with standard clinical EEG. However, apparent biomarker effects can depend on frequency-band definitions, normalization choices, aperiodic spectral structure, volume conduction, EEG reference, windowing, and validation strategy. A biomarker that produces high classification accuracy under one pipeline is not automatically a robust biological marker.

## 2.2 Primary objective

Evaluate the robustness, specificity, and predictive utility of RBP and SCC in ds004504, then engineer a reduced electrode montage that preserves the biomarker information that remains defensible.

## 2.3 Scope

| In scope | Out of scope for v1.0 |
| --- | --- |
| Eyes-closed resting EEG from ds004504 v1.0.9 | Clinical deployment or regulatory claims |
| AD, FTD, and cognitively normal groups | Prospective prediction of future dementia |
| Spectral and connectivity biomarkers | Source localization as a primary method |
| Subject-level statistics and ML | Claiming EEG directly measures synaptic strength |
| Classical ML first; DICE architecture as optional replication | Large deep-learning architecture search |
| Reduced 19-channel montage optimization | Hardware fabrication in the initial study |

## 2.4 Primary and secondary ML tasks

Primary benchmark: AD vs cognitively normal (CN), because this directly matches the principal DICE-Net benchmark.

Secondary specificity task: FTD vs CN.

Critical differential-diagnosis task: AD vs FTD.

Optional engineering task after the critique: dementia (AD + FTD) vs CN, clearly labeled as a broader screening classification rather than AD-specific detection.

# 3. Scientific Background and Research Gap

## 3.1 Dataset and DICE-Net baseline

The AHEPA/OpenNeuro dataset contains 88 eyes-closed resting-state EEG recordings: 36 Alzheimer's disease (AD), 23 Frontotemporal Dementia (FTD), and 29 cognitively normal controls (CN). Recordings use 19 standard 10-20 scalp channels and a 500 Hz sampling rate. The dataset is openly available as OpenNeuro ds004504, including raw and preprocessed data [1].

DICE-Net used RBP and SCC as dual inputs to a convolution-transformer model. Its AD-CN analysis used 30-second windows with 15-second overlap, five fixed frequency bands, and Leave-One-Subject-Out (LOSO) validation. The reported AD-CN accuracy was 83.28% [2]. DICE-Net also reported that the RBP branch received greater learned weight magnitude than SCC, while temporal and occipital channels such as T5, O1, O2, T4, and F8 were prominent for AD discrimination [2].

## 3.2 Why a critique is needed

Fixed bands can misattribute an individual alpha frequency (IAF) shift to changes in theta or alpha power.

Relative power is compositional: a change in one band changes the denominator and therefore the reported fraction in other bands.

Canonical band power can mix periodic oscillatory changes with aperiodic 1/f-like changes; spectral parameterization is designed to separate these components [4].

Magnitude coherence can be inflated by volume conduction and common sources. wPLI and imaginary coherence provide complementary tests that reduce sensitivity to zero-lag coupling [5].

A feature that separates AD from CN may also separate FTD from CN; this makes it a dementia-associated marker rather than an AD-specific marker.

Recent review of the AHEPA benchmark emphasizes that subject-level validation is essential and that epoch-level validation can produce misleadingly optimistic performance [3].

## 3.3 Synaptic/network dysfunction interpretation

Interpretation boundary: Spectral and connectivity EEG features may reflect altered network dynamics associated with neurodegeneration, synaptic dysfunction, neurotransmitter changes, and excitation/inhibition regulation. They are indirect electrophysiological correlates. This project must not state that scalp EEG directly measures synaptic loss or synaptic strength.

The synaptic-dysfunction angle is therefore best used as a mechanistic interpretation layer: if aperiodic, oscillatory, complexity, or lagged-connectivity features are robust, the discussion can relate them to circuit-level dysfunction while explicitly separating measurement from mechanism.

# 4. Research Questions, Aims, and Hypotheses

## 4.1 Main research question

Do RBP and SCC provide robust, disease-specific, and method-stable EEG biomarkers of Alzheimer's disease when individual spectral slowing, periodic/aperiodic structure, volume-conduction-sensitive connectivity, clinical severity, and FTD are explicitly considered?

## 4.2 Engineering question

What is the smallest scalp electrode configuration that preserves both subject-level machine-learning performance and the robust electrophysiological biomarkers identified by the critique?

## 4.3 Specific aims

| Aim | Description | Success criterion |
| --- | --- | --- |
| Aim 1 | Reproduce DICE-style RBP and SCC features and AD-CN discrimination. | Expected directions and plausible baseline performance under subject-level validation. |
| Aim 2 | Challenge fixed-band RBP with IAF, absolute power, and periodic/aperiodic parameterization. | Determine which spectral effects are invariant vs method-dependent. |
| Aim 3 | Challenge SCC using wPLI, debiased wPLI, imaginary coherence, and reference sensitivity. | Determine which connectivity effects survive conservative alternatives. |
| Aim 4 | Test specificity using AD-CN, FTD-CN, AD-FTD, and MMSE analyses. | Classify features as AD-specific, dementia-associated, severity-associated, or unstable. |
| Aim 5 | Compare feature families with leakage-safe ML. | Estimate out-of-sample incremental value with uncertainty. |
| Aim 6 | Optimize electrode count and placement. | Identify minimum montage satisfying pre-registered preservation criteria. |

## 4.4 Pre-specified hypotheses

H1 - Replication: AD will show spectral slowing relative to CN, including higher slow-frequency and lower alpha-related measures.

H2 - Fixed-band sensitivity: part of the apparent theta/alpha change will be altered when bands are individualized around IAF.

H3 - Spectral decomposition: some canonical band-power effects will change after periodic and aperiodic components are separated.

H4 - Connectivity sensitivity: some SCC effects will attenuate or change when using wPLI/imaginary coherence and alternative references.

H5 - Specificity: a subset of AD-CN effects will also be present in FTD-CN, indicating broader dementia/neurodegeneration associations.

H6 - ML parsimony: corrected or decomposed spectral features will provide similar or better subject-level performance than raw RBP alone without requiring a complex neural network.

H7 - Montage reduction: a sparse montage can preserve most classification information, but extreme channel reduction will lose some spatial/network biomarker information.

# 5. Dataset Specification

| Property | Specification |
| --- | --- |
| Dataset | OpenNeuro ds004504, snapshot v1.0.9 |
| Modality | Resting-state scalp EEG, eyes closed |
| Participants | 88 total: 36 AD, 23 FTD, 29 CN |
| Channels | 19 scalp channels in the international 10-20 system |
| Channel list | Fp1, Fp2, F7, F3, Fz, F4, F8, T3, C3, Cz, C4, T4, T5, P3, Pz, P4, T6, O1, O2 |
| Sampling rate | 500 Hz |
| Clinical metadata | Diagnosis, age, sex, MMSE; disease-duration metadata for patient groups where available |
| License | CC0 |
| Primary analysis data | Provided artifact-cleaned derivative EEG |
| Sensitivity analysis | Raw EEG / alternative preprocessing if time allows |

## 5.1 Reported preprocessing in the DICE-Net work

The DICE-Net paper describes a 0.5-45 Hz Butterworth band-pass filter, rereferencing to A1-A2, Artifact Subspace Reconstruction (ASR), ICA (RunICA), and ICLabel-based removal of eye/jaw artifact components [2]. For the first replication, use the distributed cleaned derivative rather than attempting to recreate the entire artifact-removal pipeline. Treat raw-data reprocessing as a later robustness experiment.

## 5.2 Metadata QC

Verify total n = 88 and group counts = 36/23/29.

Check missingness and coding in age, sex, diagnosis, MMSE, and disease duration.

Confirm no duplicated subject IDs.

Record exact dataset snapshot/DOI and file hashes if practical.

Never infer a clinical label from filenames if the BIDS metadata provides the label.

## 5.3 Dataset limitations to carry through the entire project

Cross-sectional dataset: it cannot establish prospective prediction of who will later develop dementia.

Single-center acquisition limits external generalization.

Small number of independent subjects for machine learning, regardless of how many windows are generated.

CN MMSE is at/near ceiling; all-subject MMSE correlations can be confounded by diagnosis.

Resting-state EEG is a macroscopic signal and cannot directly resolve microscopic synaptic mechanisms.

# 6. Study Design: Replication Track vs Critique Track

Figure 1. Project workflow. Replicate first; critique second; optimize electrodes last.

## 6.1 Track A - strict replication

Purpose: establish that the implementation can recreate the two feature families described by DICE-Net before any methodological changes are introduced. Track A should preserve the paper's core segmentation, band definitions, RBP calculation, SCC concept, and subject-level LOSO logic as closely as practical.

| Replication component | Specification |
| --- | --- |
| Window | 30 s |
| Overlap | 15 s (50%) |
| Internal feature time axis | 30 one-second periods |
| Bands | Delta 0.5-4; Theta 4-8; Alpha 8-13; Beta 13-25; Gamma 25-45 Hz |
| RBP | Welch PSD-derived relative band power per time x band x channel |
| SCC | Spectral coherence connectivity per time x band x channel; compute full pairwise representation and channel-averaged representation |
| Primary validation | Subject-wise LOSO for direct comparison |
| Primary task | AD vs CN |

## 6.2 Track B - critique

Purpose: change one methodological assumption at a time while holding the rest of the pipeline fixed. The critique should use paired comparisons wherever possible: the same subjects, same outer folds, same classifier, and same performance metrics. This makes differences attributable to the biomarker definition rather than to a different modeling stack.

| Baseline assumption | Challenge |
| --- | --- |
| Fixed frequency bands | Individual alpha frequency and individualized bands |
| Relative power | Absolute/log power and aperiodic-adjusted periodic power |
| Canonical narrowband power | Periodic/aperiodic parameterization |
| Magnitude coherence / SCC | wPLI, debiased wPLI, imaginary coherence |
| Single reference | Reference sensitivity analysis |
| AD vs CN only | FTD vs CN and AD vs FTD |
| Window-centric evaluation | Subject-level aggregation and equal subject weighting |

# 7. Software Environment and Repository Architecture

## 7.1 Recommended environment

conda create -n eeg_biomarkers python=3.11
conda activate eeg_biomarkers

pip install mne mne-connectivity numpy scipy pandas scikit-learn     statsmodels specparam antropy matplotlib xgboost jupyterlab     pyyaml joblib pyarrow

## 7.2 Repository structure

eeg-biomarker-critique/
|-- README.md
|-- requirements.txt
|-- environment.yml
|-- config.yaml
|-- docs/
|   |-- research_questions.md
|   |-- analysis_plan.md
|   `-- decision_log.md
|-- data/
|   |-- README.md
|   `-- processed/                 # generated; raw dataset not committed
|-- src/
|   |-- data/
|   |   |-- load_eeg.py
|   |   |-- metadata.py
|   |   `-- qc.py
|   |-- preprocessing/
|   |   |-- epoch.py
|   |   `-- reference.py
|   |-- features/
|   |   |-- rbp.py
|   |   |-- absolute_power.py
|   |   |-- iaf.py
|   |   |-- aperiodic.py
|   |   |-- coherence.py
|   |   |-- wpli.py
|   |   `-- imaginary_coherence.py
|   |-- statistics/
|   |   |-- group_analysis.py
|   |   `-- correction.py
|   |-- models/
|   |   |-- classification.py
|   |   |-- validation.py
|   |   `-- aggregation.py
|   |-- channel_selection/
|   |   |-- ranking.py
|   |   |-- forward_selection.py
|   |   `-- montage_constraints.py
|   `-- reporting/
|       |-- figures.py
|       `-- tables.py
|-- notebooks/
|   |-- 01_dataset_qc.ipynb
|   |-- 02_dice_replication.ipynb
|   |-- 03_spectral_critique.ipynb
|   |-- 04_connectivity_critique.ipynb
|   |-- 05_specificity_mmse.ipynb
|   |-- 06_ml_comparison.ipynb
|   `-- 07_channel_reduction.ipynb
|-- results/
|   |-- figures/
|   |-- tables/
|   |-- models/
|   `-- logs/
`-- tests/

## 7.3 Reproducibility rules

All analysis parameters must live in config.yaml rather than being buried in notebooks.

Notebooks should call functions from src/; notebooks are for inspection and reporting, not the sole implementation.

Every generated feature table must include subject_id and group. Window-level tables must also include window_id and start_time.

Save package versions and random seeds with each model result.

Never commit the 4+ GB dataset to GitHub. Commit download instructions and dataset DOI instead.

# 8. Data Ingestion and Quality Control

## 8.1 Loader requirements

The loader is the foundation of the project. It should find each subject's derivative EEG file, attach metadata from participants.tsv, standardize channel order, and return an MNE Raw object plus a metadata record. The exact storage path should be configurable.

def load_subject(subject_id, config):
    """Return (raw, metadata) for one subject.

    Required checks:
      - 19 expected EEG channels
      - 500 Hz sampling rate (or documented resampling)
      - finite data
      - valid diagnosis label
      - consistent channel order
    """
    ...

## 8.2 Automated QC table

| Field | Purpose |
| --- | --- |
| subject_id | Trace every sample to one independent participant |
| diagnosis | AD / FTD / CN label |
| duration_min | Identify unequal recording durations |
| sfreq | Verify sampling frequency |
| n_channels | Detect missing channels |
| missing_channels | Explicit channel QC |
| flat_channels | Low-variance/flatline flag |
| peak_to_peak_uv | Extreme-amplitude flag |
| nan_count | Data integrity |
| n_usable_windows | Downstream sample availability |
| qc_status | PASS / REVIEW / FAIL with reason |

## 8.3 Required QC figures before feature extraction

Group counts and demographic distributions.

Recording duration by subject and diagnosis.

Example 10-20 second time-series segment from at least one subject per group.

Subject PSDs from 0.5-45 Hz, with group-average PSD and dispersion.

Channel-wise variance / amplitude distribution.

Heatmap of missing or rejected channels/windows.

Stop condition: Do not proceed to ML until all 88 subjects are accounted for and every exclusion has a documented reason.

# 9. Epoching and Subject-Level Sampling

## 9.1 Replication epoching

Track A uses 30-second windows with 15-second overlap, matching DICE-Net [2]. Each 30-second window can be represented as 30 one-second feature frames for strict feature replication.

## 9.2 Independence problem

Overlapping windows are highly correlated and are never independent subjects. All splits, inferential statistics, uncertainty estimates, and headline ML metrics must respect subject identity. The AHEPA benchmark review explicitly distinguishes subject-level validation from less rigorous epoch-level validation [3].

## 9.3 Equal subject weighting

Recordings have unequal duration, so subjects generate different numbers of windows. Without correction, longer recordings contribute more training examples and more influence. Use at least one of the following strategies and report it:

Primary classical analysis: summarize window features to one subject-level vector using robust statistics (for example median, IQR, and/or trimmed mean).

Window-level model: use a subject-balanced sampler so each subject contributes approximately equally per training epoch.

Sensitivity analysis: cap or randomly sample the same number of windows per subject inside each training fold.

## 9.4 Subject-level feature table

subject_id | diagnosis | feature_family | channel | band | value
sub-001    | AD        | RBP            | O1      | alpha| ...
sub-001    | AD        | IAF            | O1      | peak | ...
...

# 10. DICE-Net Biomarker Replication

## 10.1 Relative Band Power (RBP)

For each one-second segment and channel, estimate the PSD using a Welch-style procedure and calculate band power. Replicate the DICE fixed bands: delta 0.5-4 Hz, theta 4-8 Hz, alpha 8-13 Hz, beta 13-25 Hz, gamma 25-45 Hz [2].

RBP_band = power_in_band / total_power_0.5_to_45_Hz

Output for one 30 s window:
shape = [time=30, bands=5, channels=19]

The exact denominator and Welch settings should be verified against the paper/code if available. Store the implementation choice in the decision log rather than silently assuming equivalence.

## 10.2 Spectral Coherence Connectivity (SCC)

DICE-Net describes SCC as spectral coherence between electrode pairs, followed by averaging connectivity values for each electrode, with Morlet-wavelet time-frequency estimation at representative frequencies for the five bands [2]. Implement two outputs:

Full pairwise coherence matrix per band (19 x 19) for scientific inspection.

DICE-style per-electrode averaged connectivity representation for model comparison.

## 10.3 Replication endpoints

| Endpoint | Minimum expected output |
| --- | --- |
| RBP group pattern | AD-CN scalp maps and effect sizes for each band |
| SCC group pattern | Band-specific connectivity matrices / channel summaries |
| Feature weighting sanity check | Compare spectral vs connectivity predictive contribution |
| DICE channel hypothesis | Pre-specified check of T5, O1, O2, T4, F8 prominence for AD-CN |
| Model benchmark | LOSO subject-level AD-CN baseline using RBP, SCC, and RBP+SCC |

Replication criterion: The goal is not to force 83.28% accuracy. A successful replication is a transparent implementation that produces directionally comparable biomarker patterns and a plausible subject-level baseline; differences are investigated rather than hidden.

# 11. Spectral Biomarker Critique

## 11.1 Critique A - fixed bands vs individual alpha frequency

Conventional fixed bands can be misleading when peak alpha frequency shifts. IAF itself is clinically relevant in dementia and has been associated with amyloid/neurodegenerative status and progression in larger cohorts [6]. Work on aging also shows that fixed alpha ranges can be biased when IAF slows [9].

| Method | Feature set | Question |
| --- | --- | --- |
| A. DICE fixed bands | RBP delta/theta/alpha/beta/gamma | What does the original method report? |
| B. IAF | Peak frequency in posterior/global spectrum | Does alpha slowing explain part of the RBP shift? |
| C. Individualized bands | Bands positioned relative to each subject's IAF / transition frequency | Do group effects survive personalized boundaries? |
| D. Peak features | Peak center frequency, peak power, bandwidth | Is the biological effect a peak shift, peak loss, or both? |

## 11.2 IAF estimation procedure

Compute clean subject-level PSD, initially emphasizing posterior electrodes (P3, Pz, P4, O1, O2) and also compute a global estimate.

Search a defensible alpha-peak range, e.g., 6-14 Hz, and require peak prominence above background.

If no reliable peak is detected, mark IAF as missing/unreliable rather than forcing a value.

Run sensitivity analyses for peak-detection thresholds and electrode regions.

## 11.3 Critique B - relative vs absolute power

Relative power is compositional: if theta increases, alpha relative power may decrease even if absolute alpha is unchanged. Compare at minimum:

Log absolute band power.

Relative band power.

Band ratios such as theta/alpha, clearly acknowledging their numerator/denominator dependence.

Aperiodic-adjusted periodic peak power.

## 11.4 Critique C - periodic vs aperiodic spectral structure

Parameterize power spectra using specparam or an equivalent validated implementation. Donoghue et al. showed that canonical narrowband power can conflate oscillatory peak changes with aperiodic offset/exponent changes [4].

| Component | Features to extract |
| --- | --- |
| Aperiodic | Exponent, offset, model fit quality |
| Periodic alpha | Center frequency, peak power above aperiodic background, bandwidth |
| Other periodic peaks | Theta/beta peak parameters when reliably present |
| QC | R^2 / error; number of detected peaks; failed fits |

## 11.5 Key spectral decision questions

Does AD-CN theta elevation remain after IAF adjustment?

Does apparent alpha reduction remain when peak power is measured above the aperiodic background?

Is aperiodic exponent different between groups in this dataset, and is that effect stable across electrodes?

Which corrected features distinguish AD from FTD, not only AD from CN?

Which spectral features correlate with MMSE among patients after controlling for diagnosis/age where appropriate?

# 12. Connectivity Biomarker Critique

## 12.1 Why coherence needs a stress test

Magnitude coherence can be spuriously elevated when the same source projects to multiple sensors. Vinck et al. explicitly discuss volume-conduction effects on coherence/phase-locking and introduce wPLI to improve robustness to these issues [5]. Therefore SCC should be treated as one connectivity estimator, not as ground truth connectivity.

## 12.2 Connectivity estimators

| Estimator | Role in project | Main caution |
| --- | --- | --- |
| SCC / magnitude coherence | Strict DICE replication | Sensitive to common/zero-lag sources |
| Imaginary coherence | Conservative alternative | Ignores zero-lag interactions, including potentially real ones |
| wPLI | Primary alternative phase-lag measure | Needs adequate sample length; can be noisy |
| Debiased squared wPLI | Bias-reduced sensitivity analysis | Interpretation differs from raw wPLI |

## 12.3 Analysis levels

Pairwise matrices: retain full 19 x 19 connectivity to inspect topology.

Per-electrode summary: mean connectivity from each electrode to all other electrodes for direct comparison with DICE-style inputs.

Regional summary: predefined frontal, temporal, central, parietal, occipital groupings for lower-dimensional statistical interpretation.

## 12.4 Reference sensitivity

Repeat a selected subset of connectivity analyses under at least two reference schemes when technically feasible: the distributed derivative reference and common-average reference. Do not interpret large reference-dependent changes as robust physiological connectivity.

## 12.5 Primary connectivity critique

For every DICE SCC finding, ask whether the direction and effect size remain with wPLI and/or imaginary coherence. A biomarker that exists only in magnitude coherence should be labeled method-sensitive. A feature that remains directionally consistent across estimators is stronger evidence of a robust network-level signal.

# 13. Disease Specificity and Clinical Relevance

## 13.1 Three required diagnostic contrasts

| Contrast | Interpretation |
| --- | --- |
| AD vs CN | Replicates the original Alzheimer-control setting |
| FTD vs CN | Tests whether the same biomarker is a generic dementia/neurodegeneration effect |
| AD vs FTD | Tests differential-diagnosis specificity |

## 13.2 Biomarker labels based on results

| Observed pattern | Allowed interpretation |
| --- | --- |
| AD-CN significant; FTD-CN similar; AD-FTD weak | Dementia-associated / neurodegeneration-associated marker |
| AD-CN strong; FTD-CN weak; AD-FTD strong | Candidate AD-discriminative marker |
| AD-CN only under one method/reference | Method-sensitive marker |
| Strong MMSE association across patient groups | Candidate severity-associated marker |
| High ML importance but unstable univariate biology | Predictive feature; not automatically a biological biomarker |

## 13.3 MMSE analysis

Because CN participants are at or near a ceiling MMSE of 30, an all-subject correlation can be driven primarily by diagnostic group separation. Therefore report:

All-subject correlation only as a descriptive analysis.

Primary clinical association among AD + FTD patients, optionally with diagnosis as a covariate.

Within-AD and within-FTD correlations when sample size and score range permit, with wide confidence intervals expected.

## 13.4 Confounder analysis

For leading subject-level biomarkers, fit adjusted regression models including diagnosis, age, and sex. Disease duration can be explored within patient groups. Treat MMSE as an outcome/clinical correlate rather than automatically adjusting it away from diagnostic comparisons.

# 14. Statistical Analysis Plan

## 14.1 Unit of analysis

Primary unit: The subject. Windows are repeated observations within a subject. Do not use the number of EEG windows as the sample size for group-level inferential claims.

## 14.2 Descriptive statistics

Report n, mean/SD and median/IQR for demographics and MMSE as appropriate.

Plot subject-level distributions, not only bar charts of group means.

Use bootstrap confidence intervals resampled at the subject level.

## 14.3 Group tests

For each subject-level feature, choose a pre-specified robust approach. A practical default is Mann-Whitney U plus Cliff's delta for two-group exploratory comparisons, supplemented by regression models for adjusted analyses. For approximately Gaussian log-transformed features, Welch t-tests with Hedges' g are also reasonable. The test family must be consistent and documented.

## 14.4 Multiple comparisons

The feature space can become very large (bands x channels x connectivity pairs x methods). Use Benjamini-Hochberg false discovery rate (FDR) correction within clearly defined hypothesis families. Do not pool every exploratory feature into one opaque correction family. Predefine families such as spectral replication, spectral critique, connectivity replication, and connectivity critique.

## 14.5 Recommended effect-size reporting

| Analysis | Report |
| --- | --- |
| Group difference | Effect size + 95% CI + raw p + FDR-adjusted q |
| MMSE association | Spearman rho or regression beta + 95% CI |
| Model comparison | Outer-CV metric difference + paired bootstrap/CI |
| Montage preservation | Correlation/ICC or error + retained effect size |
| Feature stability | Bootstrap selection frequency or fold selection frequency |

## 14.6 Avoiding circular analysis

Do not select electrodes on all 88 subjects and then report cross-validation performance using those same selected electrodes.

Do not select significant biomarkers using the full dataset before evaluating ML on the same subjects.

Within each outer fold, every fitted operation - scaling, imputation, feature selection, channel selection, hyperparameter tuning - must use training subjects only.

# 15. Machine-Learning Plan

## 15.1 Why classical ML first

The dataset contains 88 independent subjects. Deep models can see thousands of windows, but the biological sample size remains 88. The first objective is to compare biomarkers, not architectures. Use interpretable models before adding DICE-Net or another neural network.

## 15.2 Feature-family experiments

| Model set | Inputs | Purpose |
| --- | --- | --- |
| M0 | Age/sex only (optional) | Demographic baseline; not a diagnostic product |
| M1 | DICE RBP | Original spectral biomarker |
| M2 | DICE SCC | Original connectivity biomarker |
| M3 | RBP + SCC | Original dual biomarker |
| M4 | IAF + individualized spectral features | Fixed-band critique |
| M5 | Periodic + aperiodic spectral features | Spectral-decomposition critique |
| M6 | wPLI / ImCoh summaries | Connectivity critique |
| M7 | Robust features only | Final biomarker model |
| M8 | Robust features + reduced montage | Engineering model |

## 15.3 Algorithms

Logistic regression with regularization - primary interpretable baseline.

Linear SVM - strong small-sample baseline.

XGBoost - nonlinear comparison, carefully tuned inside inner CV.

Optional DICE-Net reimplementation - only after feature analyses are stable, primarily as a benchmark rather than the central contribution.

## 15.4 Metrics

| Metric | Use |
| --- | --- |
| Balanced accuracy | Primary when class counts differ |
| ROC-AUC | Ranking performance |
| Sensitivity | Patient detection rate |
| Specificity | Control rejection rate |
| F1 | Precision-recall balance |
| MCC | Useful balanced summary for small binary datasets |
| Calibration / Brier score | Optional probability-quality analysis |

## 15.5 Subject-level prediction

If a model is trained on windows, generate a probability for each window and aggregate probabilities within each held-out subject (mean or median fixed in advance). Calculate the headline metrics once per subject. Also report sensitivity to aggregation choice as a secondary analysis.

# 16. Validation and Leakage Prevention

Figure 2. Validation firewall. Test subjects remain untouched until final outer-fold evaluation.

## 16.1 Direct replication validation

Use LOSO for a direct DICE-style benchmark. Every window from the held-out subject belongs to the test set; none can appear in training or validation.

## 16.2 Main final validation

Use nested subject-wise cross-validation for the final feature and montage comparisons. A practical setup is outer StratifiedGroupKFold (for example 5 folds, repeated if computationally feasible) with inner subject-wise CV for hyperparameters and selection. With only 88 subjects, confidence intervals and fold variability are essential.

## 16.3 Leakage checklist

Group splits by subject_id, never by window_id.

Fit scaler only on outer-training data.

Fit missing-value imputer only on outer-training data.

Select biomarkers only on outer-training data.

Select electrodes only on outer-training data.

Tune model hyperparameters only in inner CV.

Do not choose the probability threshold using outer-test predictions.

Do not use the full dataset to decide a montage and then treat CV performance as unbiased.

## 16.4 Unequal-duration leakage/weighting issue

Because recordings differ in duration, the number of windows per subject must not implicitly act as a sample weight unless this is intentionally designed. Use subject-balanced sampling or subject-level feature summaries, and repeat the main result with equal windows per subject as a sensitivity analysis.

# 17. Robust Biomarker Decision Framework

A feature should not be called a robust biomarker merely because it is significant or highly ranked by a classifier. Use a multi-criterion evidence table.

| Criterion | Question | Possible status |
| --- | --- | --- |
| Replication | Does it reproduce the DICE-style AD-CN direction? | Pass / fail / mixed |
| Effect size | Is the subject-level difference practically meaningful? | Small / medium / large with CI |
| Method stability | Does it survive RBP vs absolute/IAF/aperiodic changes? | Stable / sensitive |
| Connectivity stability | Does it survive SCC vs lagged measures/reference? | Stable / sensitive |
| Specificity | Does it distinguish AD from FTD? | AD-specific / dementia-associated / unclear |
| Clinical relevance | Is it associated with MMSE among patients? | Supported / unsupported / uncertain |
| Predictive increment | Does it improve nested-CV performance beyond simpler features? | Adds value / redundant |
| Selection stability | Is it repeatedly selected across folds/bootstraps? | Stable / unstable |

## 17.1 Proposed classification of final features

Tier A - robust: consistent biology, method stability, reasonable uncertainty, and either clinical or predictive relevance.

Tier B - useful but non-specific: robust dementia-related signal without AD-vs-FTD specificity.

Tier C - predictive only: improves ML but lacks stable physiological interpretation.

Tier D - method-sensitive: direction/effect changes substantially with frequency definitions, reference, or connectivity estimator.

Important: Do not collapse these dimensions into one arbitrary score unless the score and weights are pre-specified. A transparent evidence matrix is usually more defensible than a single biomarker score.

# 18. Minimal-Electrode Optimization

## 18.1 When this stage starts

Electrode optimization begins only after Tier A/B biomarker families have been defined. This prevents the montage from being optimized to artifacts of the original feature definitions.

## 18.2 Candidate strategies

| Strategy | Description | Role |
| --- | --- | --- |
| Single-channel screen | Estimate performance / biomarker utility from each channel alone | Interpretability and sanity check |
| Sequential forward selection | Add the channel that gives the greatest training-fold improvement | Primary data-driven sparse search |
| Backward elimination | Remove the least useful channel iteratively | Cross-check selection path |
| Predefined anatomical montages | Frontal, posterior, temporal, midline, bilateral sparse sets | Clinical/practical comparison |
| DICE hypothesis montage | Test high-attention channels reported by DICE: T5, O1, O2, T4, F8 | Literature-informed baseline |

## 18.3 Do not optimize accuracy alone

For electrode subset S, track at least two dimensions:

Diagnostic preservation:
Delta_BA(S) = BA_19ch - BA_S

Biomarker preservation:
compare subject-level biomarker values/effect sizes under S vs 19 channels
(e.g., correlation, absolute error, retained standardized group effect).

## 18.4 Example design requirement

Before inspecting final test-fold results, define a minimum viable montage criterion. A reasonable candidate to discuss with a mentor is: balanced accuracy within 2 percentage points of the full montage AND high biomarker preservation (for example correlation >= 0.90 for designated subject-level summary biomarkers), with no major loss of the key AD-CN effect size. The final thresholds must be fixed before final evaluation, not chosen after seeing the curve.

## 18.5 Practicality constraints

Electrode count.

Spatial spread and setup complexity.

Hair-bearing vs forehead/accessible locations.

Whether connectivity features require paired regions that are lost in an ultra-sparse montage.

Whether the montage is stable across outer folds or changes wildly.

## 18.6 Primary final plot

Plot outer-CV balanced accuracy and biomarker preservation against electrode count (19, 12, 8, 6, 4, 3, 2). Show uncertainty, not only the mean. Mark the smallest subset meeting the pre-specified requirements.

# 19. Sensitivity and Robustness Analyses

| Sensitivity analysis | Reason |
| --- | --- |
| 30 s overlapping vs non-overlapping windows | Check dependence on augmentation/overlap |
| 10 s / 60 s windows | Check time-scale sensitivity |
| Subject-level median vs mean aggregation | Check robustness to outlier windows |
| Equal windows per subject | Remove recording-duration weighting |
| Posterior IAF vs global IAF | Check alpha-peak definition |
| Alternative peak-detection thresholds | Check IAF/specparam fit dependence |
| Relative vs log absolute power | Check compositional normalization |
| Distributed reference vs common average | Check reference sensitivity |
| SCC vs wPLI vs ImCoh | Check volume-conduction-sensitive interpretation |
| Age/sex adjusted vs unadjusted | Check demographic confounding |
| AD-CN / FTD-CN / AD-FTD | Check disease specificity |
| Different outer-CV seeds/folds | Check model-selection stability |

## 19.1 Optional advanced extensions

Permutation testing of subject-level classification performance.

Stability selection for channels/features across bootstrap resamples.

Calibration and decision-curve analysis, clearly labeled exploratory.

Raw-vs-derivative preprocessing sensitivity.

Graph-level features derived from lagged connectivity, only after pairwise measures are validated.

# 20. Figures, Tables, and Reporting Standards

## 20.1 Minimum final figures

| Figure | Content |
| --- | --- |
| Fig. 1 | Project workflow |
| Fig. 2 | Dataset/QC summary |
| Fig. 3 | Group-average PSD with subject dispersion |
| Fig. 4 | Fixed-band RBP scalp maps |
| Fig. 5 | IAF distributions and individualized spectral comparison |
| Fig. 6 | Periodic vs aperiodic decomposition examples and group results |
| Fig. 7 | SCC vs wPLI/ImCoh connectivity comparison |
| Fig. 8 | AD-CN, FTD-CN, AD-FTD biomarker effect-size matrix |
| Fig. 9 | Nested-CV feature-family performance |
| Fig. 10 | Electrode importance / selection frequency topomap |
| Fig. 11 | Performance and biomarker preservation vs electrode count |

## 20.2 Minimum final tables

| Table | Content |
| --- | --- |
| Table 1 | Participant characteristics and missing data |
| Table 2 | All preprocessing and feature parameters |
| Table 3 | Replication RBP/SCC group effects |
| Table 4 | Spectral critique results |
| Table 5 | Connectivity critique results |
| Table 6 | Specificity + MMSE evidence matrix |
| Table 7 | ML models and outer-CV metrics with CIs |
| Table 8 | Final biomarker tier assignment |
| Table 9 | Candidate montages and preservation metrics |

## 20.3 Reporting conventions

Always report independent subject n alongside any number of windows.

Report confidence intervals for key effects and performance metrics.

Separate exploratory analyses from pre-specified analyses.

State exactly where feature/channel selection occurs in CV.

Use "classification" or "discrimination" rather than "diagnosis" when describing model output.

Do not call a signal AD-specific without an AD-vs-FTD test.

# 21. Milestones and Execution Order

| Milestone | Work | Gate before continuing |
| --- | --- | --- |
| M1 - Environment | Repo, environment, config, dataset snapshot | Code runs from clean environment |
| M2 - Ingestion/QC | Load 88 subjects, metadata, QC report | All subjects accounted for |
| M3 - DICE features | RBP + SCC replication | Feature values/plots validated |
| M4 - Spectral critique | IAF, absolute power, specparam | QC of peaks/fits complete |
| M5 - Connectivity critique | wPLI, ImCoh, reference checks | Estimator outputs validated |
| M6 - Specificity/clinical | AD/FTD/CN + MMSE | Effect-size matrix complete |
| M7 - ML benchmark | Nested subject-wise CV | No leakage; uncertainty reported |
| M8 - Biomarker decision | Tier A-D classification | Robust set locked |
| M9 - Montage optimization | Nested channel selection | Minimum montage identified |
| M10 - Final reporting | Figures, paper-style report, README | Reproducible from config |

## 21.1 First seven working days

| Day | Concrete deliverable |
| --- | --- |
| 1 | Repository, environment, dataset v1.0.9, participants.tsv loaded |
| 2 | load_eeg.py + metadata.py; inspect sub-001 end-to-end |
| 3 | qc.py; full 88-subject QC table and PSD report |
| 4 | 30 s / 15 s epoching with subject IDs preserved |
| 5 | RBP extractor and unit tests on synthetic signals |
| 6 | SCC extractor; full pairwise matrix + per-channel summary |
| 7 | First AD-CN replication plots and subject-level effect-size table |

# 22. Risk Register and Mitigation

| Risk | Consequence | Mitigation |
| --- | --- | --- |
| Epoch leakage | Artificially high accuracy | Group all splits by subject; automated split assertions |
| Unequal windows per subject | Long recordings dominate | Subject-level summaries or balanced sampler |
| Overfitting 88 subjects | Unstable model / channel set | Simple models, nested CV, regularization, CIs |
| Feature explosion | Multiple-testing/selection instability | Predefined families, FDR, dimensional summaries |
| IAF missing/weak peaks | Biased individualized-band subset | Explicit fit QC; report missingness; sensitivity analysis |
| Coherence volume conduction | False connectivity interpretation | wPLI/ImCoh and reference sensitivity |
| Channel selection leakage | Optimistic reduced-montage results | Selection entirely inside outer training folds |
| Clinical overclaim | Invalid interpretation | Use discrimination terminology; state cross-sectional limits |
| Replication mismatch | False criticism of DICE | Separate strict replication and critique tracks |
| Software/version drift | Non-reproducible results | Pin environment and record package versions |

# 23. Reproducibility, Ethics, and Claims

## 23.1 Data ethics

The analysis uses a public, de-identified, CC0 research dataset. Preserve the dataset citation and original ethical provenance. Do not attempt re-identification. Keep downloaded data outside the Git repository.

## 23.2 Reproducibility record

Dataset DOI and snapshot version.

Git commit hash for each final result.

environment.yml / requirements lock file.

config.yaml archived with results.

Random seeds.

Outer/inner fold subject IDs saved as machine-readable files.

Feature definitions, frequency boundaries, references, and QC thresholds recorded.

## 23.3 Claim language

| Avoid | Prefer |
| --- | --- |
| "The model diagnoses Alzheimer's disease." | "The model discriminates AD from CN within this dataset." |
| "EEG measures synaptic dysfunction." | "EEG features are indirect electrophysiological correlates potentially related to circuit/synaptic dysfunction." |
| "This is an early Alzheimer detector." | "This cross-sectional model distinguishes already diagnosed groups." |
| "SCC measures brain connectivity." | "SCC is a sensor-level coherence measure that can reflect both neural coupling and common-source/volume-conduction effects." |
| "Feature X is an Alzheimer biomarker." | "Feature X is an AD-associated candidate biomarker unless specificity and external validation are demonstrated." |

# 24. Definition of Done

## 24.1 Scientific completion

DICE-style RBP and SCC are replicated with documented parameters.

Fixed vs individualized frequency analysis is complete.

Relative vs absolute vs aperiodic-adjusted spectral analysis is complete.

SCC is compared with wPLI and imaginary coherence.

AD-CN, FTD-CN, and AD-FTD are all evaluated.

MMSE relationships are evaluated primarily within patients.

Final biomarker evidence tiers are assigned with uncertainty.

## 24.2 ML completion

All headline metrics are subject-level.

Nested subject-wise validation is used for the final model comparison.

No preprocessing, feature selection, or channel selection uses outer-test data.

Feature-family comparisons use matched folds.

Model uncertainty and selection stability are reported.

## 24.3 Engineering completion

Electrode-selection algorithm runs inside training folds.

At least one literature-informed and one data-driven sparse montage are compared.

Performance-vs-channel-count curve includes uncertainty.

Biomarker-preservation-vs-channel-count curve includes uncertainty.

The final montage is chosen using a pre-specified criterion and practical considerations.

## 24.4 Documentation completion

README enables another researcher to obtain the data and rerun the pipeline.

Every final figure can be generated from code, not manually edited values.

The methods section can be reconstructed from config files and decision log.

Limitations and non-causal interpretations are stated clearly.

# Appendix A. Configuration Template

project:
  seed: 42
  results_dir: results

dataset:
  id: ds004504
  version: 1.0.9
  root: /path/to/ds004504
  use_derivatives: true

channels:
  expected: [Fp1, Fp2, F7, F3, Fz, F4, F8, T3, C3, Cz, C4, T4,
             T5, P3, Pz, P4, T6, O1, O2]

epoching:
  length_sec: 30
  overlap_sec: 15
  subwindow_sec: 1

bands:
  delta: [0.5, 4]
  theta: [4, 8]
  alpha: [8, 13]
  beta:  [13, 25]
  gamma: [25, 45]

features:
  rbp: true
  absolute_power: true
  iaf: true
  specparam: true
  scc: true
  wpli: true
  imaginary_coherence: true

iaf:
  search_range_hz: [6, 14]
  region: posterior
  channels: [P3, Pz, P4, O1, O2]

validation:
  replication: LOSO
  final_outer_folds: 5
  final_inner_folds: 4
  group_key: subject_id
  primary_metric: balanced_accuracy

models:
  logistic_regression: true
  linear_svm: true
  xgboost: true

channel_selection:
  method: sequential_forward
  candidate_counts: [19, 12, 8, 6, 4, 3, 2]
  selection_inside_cv: true

All values above are starting specifications. Any parameter changed after inspecting results must be recorded in docs/decision_log.md, with the reason and whether the change makes the analysis exploratory.

# Appendix B. Command-Line Workflow

# 1) Validate environment and configuration
python -m src.data.metadata --config config.yaml

# 2) Build subject QC report
python -m src.data.qc --config config.yaml

# 3) Create epoch index (do not duplicate raw arrays unnecessarily)
python -m src.preprocessing.epoch --config config.yaml

# 4) Replicate DICE features
python -m src.features.rbp --config config.yaml
python -m src.features.coherence --config config.yaml

# 5) Spectral critique
python -m src.features.iaf --config config.yaml
python -m src.features.aperiodic --config config.yaml

# 6) Connectivity critique
python -m src.features.wpli --config config.yaml
python -m src.features.imaginary_coherence --config config.yaml

# 7) Subject-level statistics
python -m src.statistics.group_analysis --config config.yaml

# 8) ML comparison
python -m src.models.classification --config config.yaml

# 9) Channel reduction (only after robust feature set is locked)
python -m src.channel_selection.forward_selection --config config.yaml

# 10) Regenerate all final figures/tables
python -m src.reporting.figures --config config.yaml
python -m src.reporting.tables --config config.yaml

# Appendix C. Data Dictionaries

## C.1 Subject metadata

| Column | Type | Meaning |
| --- | --- | --- |
| subject_id | string | Unique BIDS subject identifier |
| diagnosis | categorical | AD / FTD / CN |
| age | numeric | Age in years |
| sex | categorical | Dataset-coded sex |
| mmse | numeric | Mini-Mental State Examination score |
| disease_duration_months | numeric/NA | Patient disease duration when available |
| qc_status | categorical | PASS / REVIEW / FAIL |

## C.2 Window index

| Column | Meaning |
| --- | --- |
| subject_id | Independent participant identity |
| window_id | Unique within-subject window |
| start_sec | Window onset |
| stop_sec | Window end |
| diagnosis | Group label copied from metadata |
| usable | QC flag |
| reject_reason | Reason for exclusion if unusable |

## C.3 Feature table

| Column | Meaning |
| --- | --- |
| subject_id | Subject identity |
| window_id | Window identity or SUBJECT for aggregated data |
| feature_family | RBP / IAF / APERIODIC / SCC / wPLI / ImCoh |
| channel_or_pair | Electrode or electrode pair |
| band | Frequency band if applicable |
| value | Feature value |
| method_version | Feature implementation/version string |
| qc_flag | Fit/reliability status |

# Appendix D. Analysis Checklists

## D.1 Before feature extraction

[ ] Dataset version recorded as ds004504 v1.0.9

[ ] 88 unique subjects loaded

[ ] Group counts verified: AD 36, FTD 23, CN 29

[ ] 19 expected channels verified

[ ] Sampling rate checked

[ ] Duration distribution reviewed

[ ] Flat/missing/extreme channels reviewed

[ ] QC exclusions documented

## D.2 Before statistics

[ ] Feature QC completed

[ ] Subject-level aggregation defined

[ ] Hypothesis families defined for FDR

[ ] Primary contrasts fixed

[ ] Effect-size measure fixed

[ ] MMSE primary population fixed (patients)

## D.3 Before ML

[ ] Group key = subject_id

[ ] Outer folds saved

[ ] Inner CV configured

[ ] Scaling inside pipeline

[ ] Imputation inside pipeline

[ ] Feature selection inside inner CV

[ ] Subject-level headline metrics

[ ] Equal-subject weighting strategy documented

## D.4 Before montage optimization

[ ] Robust biomarker set locked

[ ] Minimum viable montage thresholds pre-specified

[ ] Channel selection is nested

[ ] Literature-informed montage defined before results

[ ] Practical montage constraints documented

[ ] Performance + biomarker preservation both reported

# References

[1] A. Miltiadous et al., "A dataset of EEG recordings from: Alzheimer's disease, Frontotemporal dementia and Healthy subjects," OpenNeuro dataset ds004504, snapshot v1.0.9. DOI: 10.18112/openneuro.ds004504.v1.0.9.

[2] A. Miltiadous, E. Gionanidis, K. D. Tzimourta, N. Giannakeas, and A. T. Tzallas, "DICE-Net: A Novel Convolution-Transformer Architecture for Alzheimer Detection in EEG Signals," IEEE Access, vol. 11, pp. 71840-71858, 2023. DOI: 10.1109/ACCESS.2023.3294618.

[3] A. Miltiadous et al., "The AHEPA EEG benchmark: setting the standard for machine learning in dementia diagnosis, a scoping review," Cognitive Neurodynamics, vol. 20, art. 95, 2026. DOI: 10.1007/s11571-026-10464-w.

[4] T. Donoghue et al., "Parameterizing neural power spectra into periodic and aperiodic components," Nature Neuroscience, vol. 23, pp. 1655-1665, 2020. DOI: 10.1038/s41593-020-00744-x.

[5] M. Vinck, R. Oostenveld, M. van Wingerden, F. Battaglia, and C. M. A. Pennartz, "An improved index of phase-synchronization for electrophysiological data in the presence of volume-conduction, noise and sample-size bias," NeuroImage, vol. 55, no. 4, pp. 1548-1565, 2011. DOI: 10.1016/j.neuroimage.2011.01.055.

[6] "Analysis of individual alpha frequency in a large cohort from a tertiary memory center," European Journal of Neurology, 2024. PMID: 39087560.

[7] C. Babiloni et al., "Measures of resting state EEG rhythms for clinical trials in Alzheimer's disease: Recommendations of an expert panel," Alzheimer's & Dementia, 2021. PMID: 33860614.

[8] M. Kopcanova et al., "Resting-state EEG signatures of Alzheimer's disease are driven by periodic but not aperiodic changes," Neurobiology of Disease, vol. 190, 106380, 2024. DOI: 10.1016/j.nbd.2023.106380.

[9] "Resting-state EEG power and connectivity are associated with alpha peak frequency slowing in healthy aging," Neurobiology of Aging, 2018. PMID: 30144647.

[10] G. Ozbek et al., "Resting-state EEG alpha/theta power ratio discriminates early-onset Alzheimer's disease from healthy controls," Clinical Neurophysiology, vol. 132, 2021. DOI: 10.1016/j.clinph.2021.05.012.

Document status: This is a complete execution blueprint, not a frozen statistical protocol. Before final hypothesis testing, convert the chosen thresholds, feature definitions, and primary models into a short pre-analysis plan and lock it in version control.